Jawahar Bala Aarogya Raksha Government of AP.

De-worming for total population - 29th January 2013.

Program implementation Guidelines.

1. Introduction

Anemia is preventable medical condition observed in AP. The worm infestation is one of the common causes of Anemia especially in the population living in the rural, tribal areas, urban slums and in those who are below poverty line. In AP 71% children between the age of 6 and 59 months, 66% of adolescents, 59% of pregnant and 73% of lactating women are anemic and overall 63% of women and 23% men are anemic ( NHHS-3).

To address this problem GOAP has decided to administer De-worming medicines to the total population of the state. The program scheduled to be implemented on 29th January 2013.

The departments of Health, Education, ICDS, Rural Development, Panchayati Raj, Tribal welfare, BC & Social welfare shall take an active role in the implementation of the program and provide active support in communicating the program objectives to the grass root functionaries and the beneficiaries. The functionaries of these departments shall ensure the administration of De-worming tablet to all.

2. Departments involved in planning & implementation:

Health, Education, ICDS, Rural Development, Panchayati Raj, Tribal welfare, BC & Social welfare departments shall take part in planning at district level and sensitize the functionaries on De-worming for all & take up all the necessary actions to implement the program.

3. Program Activities at District, Mandal , village /habitation level.

3.1. District level Activities:

1.DMHO shall involve PO ITDA, ZP-CEO, PD DRDA/IKP, PD ICDS, DEO, PORVM, DCHS, Municipal commissioners, superintendent of Medical colleges, all program officers , 104, 108 coordinators, JBAR coordinators ( Health &education ), DD adult education, Municipal health officers, JD SWD, DD TWD, DD BCW, AD Disabled, Minorities welfare, Dy.EOs, RVM & SOs while planning at district level under the chairmanship of district collector and sensitize the functionaries on de-worming day and allocate responsibilities as monitors/observers during administration of De worming tablets / syrup to total population in the district.

2. DMHO will prepare the action plan in consultation with the concerned line departments for administration of de-worming medicines and take approval for the same from district collector.

3. DMHO will ensure focused action plan for tribal area under the chairman ship of PO ITDA.

4. Circulate the approved plan of action to all concerned district functionaries to disseminate the same up to grassroots level functionaries.

5. Once the plan is approved by the district collector, district officers of Health, ICDS , Education and DRDA will sensitize the ZMS ( Zilla Mahila Samakhya) Members about De-worming day and the role of samakhya members in mobilizing the community in successful administration of De worming by 1st week of January.

6. ZMS members will orient the (MMS) Mandal Mahila samakhya members during MMS meetings. In turn MMS members will orient the VOs, Health activists and health subcommittee members about De-worming day and their role in community mobilization to cover all for successful administration of De-worming tablets.

7. DMHO will ensure the availability of sufficient quantity of required drugs at CHNC level by 15th January for further distribution to PHCs/UHCs.

8. SPHO will ensure the availability of sufficient quantity of required drugs at PHC/UHC level by 20th January.

3.2. Mandal Level Activities:

1.MO PHC/UHC will prepare Mandal level action plan for distribution of drugs and ensures the availability of sufficient quantity of required drugs at AWCs, Schools/colleges and Gram Panchayati/Municipal ward by 25th January as per the action plan prepared at PHC/UHC level for administration of De worming Tablets.

2. Mandal health coordinators (MEO, MOs)will coordinate convergence meetings at Mandal level under the chairmanship of MPDO with all the staff from Health, Education, ICDS,RWS and IKP(MMS).

3. Allocate responsibilities to all CHOs, MPHEOs, HEOs, CRPs, Mandal Coordinators, Teachers, Welfare officers, IKP coordinators, MPHS(M/F), MPHA(M/F) and NGOs working in the mandal for successful implementation of the program.

4. Ensures Village/Habitation level action plan for administration of De-worming by the end of the meeting

3.3. Village /Habitation Level Activities:

1. Habitation level Action plan will be prepared during mandal level convergence meeting by involving all the concerned departmental functionaries under the chairmanship of mandal health coordinators for administration of De-worming tablets.

2. They shall plan using School, AWC and Gram Panchayati as the platforms/places for administration of De worming tablets on 29th January.

3. School health coordinators (HMs and paramedical staff) and principals with the support of AWWs and ASHAs are responsible for Habitation level De worming tablets administration.

4. VOs, Health activists, SMC, Health sub committees are responsible for mobilization of communities for accessing the de-worming tablets.

5. Drop outs and Missed outs will be covered on the next day i.e on 30th January during house to house verification by AWW, ANM, Teacher, swachaata doot, ASHA and VO.

Panchayat/Muncipal ward wise plan of action for De-worming

1. Name of the District:					2.Name of the Mandal:

3. Name of the GP/Municipal Ward:			4. Name of the Habitation/Catchment area:

5. Door No: From-------      To------

| Sl. | Door no | No of persons in the households | No of persons administered De-worming tab on 29th | No of persons administered De-worming tab on 30 th Jan 13 | Designation of the Responsible Person & Contact No | Designation of the Supervisor/ Contact No |
| --- | --- | --- | --- | --- | --- | --- |

Note: Habitation/ catchment area list is available at District RVM office.

Signature of the Mandal Health Coordinators - MEO: 				MO:

4. Functionaries roles and the responsibilities:

4.1. Head masters, principals, village secretary, ward members, VOs, SwachchataDoot, ASHAs                            and AWWs shall ensure the following activities in schools, colleges, Gram Panchayati and AWCs .

- Ensure 100 percent attendance on the day of activity…

  - Educate students, community members on importance of de-worming activity from 25th Jan, 2013 in different available platforms.

  - Conduct Parents –Teachers Association (PTA)/SMC  meetings in schools and colleges one week prior to the day of administration

  - Village secretary and ward members will ensure communication of De worming day and its importance through DANDORA at habitation level.

  - AWWs and ASHAs will conduct mothers meetings on NHDs and educate mothers on the importance of De-worming.

  - VOs and SHGs will discuss about importance of De-worming and the role of HAs, HSCs and VOs in mobilizing the communities on the day of de-worming day during group meetings.

- Educate all students and community members to attend the venues after consumption of food for taking the De-worming tablets

- Ensure sanitation in and around the school, college and GP and AWC premises.

- Ensure availability of running water to available toilets.

- Provide safe drinking water with disposable glasses.

- Provide balanced diet during mid day meal in a congenial atmosphere.

- On 29th -01-2013 Head Masters/Principals will ensure:

- Proper hand washing of all students with soap and water,

- Providing mid-day meal in clean utensils,

- Administration of de-worming tablets to teachers, AWWs, workers, cook, Kamati Watchman, ward members and village secretary first and then to students and other community members After the meal.

4.2    CEO-ZP shall:

1.  Instruct MPDOs to take up the de-worming program in the mandals.

2.  Instruct MPDOs to coordinate/converge with all line departments for effective implementation of the program in the mandal.

4.3    Municipal Commissioners of Municipal Corporations shall:

1. Instruct Health Officers to take up de-worming program in municipal areas,

2. Instruct DI of schools and CRPs to take up the de-worming program in all municipal schools.

3. Municipal Health Officers and DI of schools can coordinate with JBAR Coordinators in the District.

4.4    DM&HOs shall:

1. Conduct district task force meeting under the chairman ship of District Collector with SPHOs and all line departments in the first week of January, 2013.

2. Allot areas of supervision to all program officers as it is being done in the case of PPI program to monitor the de-worming program,

3. Provide POL budget from available school health program Rs. 1000/- to each Program Officer who are having Govt. Vehicles and Rs. 1500/- to other POs who are not having Govt. Vehicles to monitor the program.

4. Provide mobility budget from available school health program Rs. 1000/- to PHC/UHC Medical Officer.

5. Ensure distribution of drugs by CHNCs (SPHOs) as per requirement to all PHC/UHCs.

6. Ensure coordination between MO-PHC/UHCs, MEOs and ICDS representatives of the mandal for proper distribution of the drug in the mandal.

7. Make necessary arrangements to collect reports through SPHOs from periphery, compile and submit to the state on the same day.

8. Conduct Press Meets along with DEO, PO-RVM,PD ICDS and PD DRDA by involving Print and Electronic Media to brief the importance of de-worming day.

4.5. DEO/PO-RVM/DD Adult Education, PD ICDS and PD DRDA shall

1. Instruct Dy EOs/ Sectoral officers to monitor respective areas to monitor /supervise the schools regarding the importance of the program.

2. Instruct MEOs /CRPs/Mandal coordinators /special teachers to involve in the program and to cover all schools and colleges (KGBV and Work site schools).

3. Ensure coordination between MEOs and MO-PHC/UHCs, ICDS representatives and MMS representatives of the mandal for proper distribution of the drug in the mandal, and to cover all students and community members.

4.6. Medical Officers :

1. Medial officers are responsible in ensuring the availability of school wise student list in coordination with MEO/CRPs for proper distribution of Drugs.

2. Ensures habitation/Catchment wise list of families along with the list of individuals in coordination with AWWs. Notified Habitation/Catchment is available in the RVM Office

3. Medical officers have to supply sufficient number of Cetrizine and Prednisalone tablets to all paramedical staff to treat any emergency cases along with De-worming tablets.

4.Rs.1000/- will be provided by  DM&HO for mobility of MO  and his team to utilize on the  day of drug administration and MO is instructed to keep emergency drugs and IV fluids with him/her,

5.MOs have to supervise the program and also to attend any emergency.

6. MOs are instructed to inform to 104 and 108 coordinators regarding this program and to take their support,

7. If any adverse reactions, need to be intimated to DM&HO/JBARC’s (Health/Education),

8.  MOs are instructed to coordinate with MPDO, MEO and other line departments for successful implementation of the program.

9. SPHOs are instructed to coordinate with MOs and MEOs and other departments for Successful implementation and effective monitoring. Cluster wise they are the responsible persons.

5. De worming drug administration Program Activities:

5.1.Before the Day of De-worming: i.e. on 28.01.2013

- Coordination of Health, ICDS, School Staff and Mahila Samakhya members in mobilizing the students and community members for the De-worming Day and make sure 100% attendance.

- Involve formal & informal local leaders to make the program success.

- SPHOs to ensure all the logistics in place for proper administration of De-worming  tablets in their concerned area ( in all habitations ) and send report to the Districts.

- SPHOs to Inform 108 &104 Services to attend the emergency cases on top priority if any.

- Ensure availability of Drugs.

- Make sure Schools and colleges { govt, aided, private ( recognized and registered) }, GP , AWC premises and toilets are clean.

- Make sure provision of safe drinking water.

- Make sure provision of soap and water to demonstrate the hand washing practices.

- The HMs, GP members, school and AW teachers are requested to inform and utilize 108 in case of any emergency and inform to District Coordinator.

5.2.On the Day of De-worming 29.01.2013

Should ensure the following activities in all the venues where the Deworming tablets will be administered

| 1 | 8.00 AM to 10.00 AM - | The Concern AWWs, Teachers, School Staff and medical team, Swachcsshata Doot should mobilize students and other community members with the support of VOs, HAs, HSCs, and make all arrangement for administration of Drugs. |
| --- | --- | --- |
| 2 | 10.00 AM to 12.00 NN | Health Education to all students and other community members on personal hygiene and sanitation. |
| 3 | 12.00 NN to 12.30 PM | Create awareness on Iron rich foods, Vitamin C rich foods & Balanced Diet. |
| 4 | 12.30 PM to 1.30 PM | Ensure consumption of food at school and house hold level by all individuals before the administration of Deworming Tablet. |
| 5 | 1.30 PM to 2.30 PM | Administer De-worming tablets with safe drinking water first to teachers, MDM Staff, Higher class students and then to the lower class students. Administer De-worming tablets with safe drinking water first to AWWs, VOs, HAs, HSCs, ASHAs and then to all community members. |
| 6 | 2.30 PM to 5.00 PM | Observe any reactions and attend immediately by utilizing the services of 108 and all government vehicles. After competition of activity send the report in prescribed format to the concern PHC/UHC. |

5.3.After the Day of De-worming: i.e. on 30.01.2013

- Drop outs and Missed outs will be covered on the next day i.e on 30th January during house to house verification by AWW, ANM, Teacher, swachaata doot, ASHA and VO.

- MO/MEO and all School Health Coordinators make sure that there is no reaction due to administration of De-worming tablets.

- MO/MEO and all School Health Coordinators make sure that Drop outs and Missed outs will be covered in all catchment area/habitations in the mandal on 30th January.

- Consolidate and confirm the reports and furnish to O/o. CH&FW from the Districts (jbar.state@gmail.com).

- Submit the voucher and SOEs to the district within 3 days.

- Final Utilization Certificate and SOEs have to be furnished within a week to the 
O/o CH&FW.

Monitoring and Reporting:

On the day of drug administration and mopping up operations, it must be supervised to ensure that the drug is physically administered to each and every individual. The supervisor should ensure that no area/ village/habitation is omitted. The cross checking report by the supervisors must be submitted to the MO PHC/UHC, CDPO and MEO.

MPDO and the municipal commissionaires in urban areas are responsible to ensure the monitoring visits by the concerned departments and submission of reports.

Monitoring format for De-worming Drug Administration

Name of the Panchayat/ Muncipal ward:

| Sl | Name of the Habitation/ catchment area | Total No. of Houses | No. of households surveyed | Total number of persons in the House holds | No. of persons consumed De worming tablet | Side reactions if Any |
| --- | --- | --- | --- | --- | --- | --- |

Date:			Name and Designation of the Supervisory Officer:

MO PHC/UHC, MPDO, Municipal commissioner and SPHO are responsible for the reporting of the total deworming administration and ensure the reports reached to district DMHO/JBAR cell by 31st January.

Reporting Format for De-worming Drug Administration

Name of the District:				Name of the Mandal:

Name of the CHNC:				Name of the PHC:

Date of Reporting:

| Sl | Name of the Sub centre | Total Population | No. of tablets supplied | No of tablets administered | Balance tablets at SC level | No of Nutrition and Health education sessions conducted |
| --- | --- | --- | --- | --- | --- | --- |

Name and Designation of Supervisory Officer:

***