JAWAHAR BALA AROGYA RAKSHA

andhra Pradesh

Swasthh on Wheels Guidelines

(Chakraalapai Aarogyam)

Lr.Rc.No. /SHP/2012/13						    Date:27.10.2012

Swasthh on wheels is going to be launched on Nov 2012 to create awareness among students and parents community regarding sanitation, nutrition,WIFS, Health hygiene by involving the Department of Medical and Health Education, ICDS, Panchayat Raj, NGO’s, Local leaders, parents, school health coordinators, ASHAs and Swachchata Doot / RWS.

District level Action Plan to implement the Swasthh on wheels.

- Activities to be under taken:

A Vehicle to be arranged at district and decorated with flexes, Public Address System (PAS), CDs, Video Film, IEC, Pamphlets etc., has to cover all the  PHC/UHC of the districts  to propagate the SWASTHH on Wheels  activities covering one to two Health Centers per day.

- The activities to be taken of Two days before the programme

At the Mandal Level the School Health Coordinators i.e. Medical Officer (PHC) and Mandal Education Officer has to convene meeting with the Mandal level officers such as MPDO, Tahasildar, CDPO, Local political & community leaders, MMS and RWS engineers etc. and prepare the action plan to implement the SWASTHH on Wheels at the mandal level.  The Press conference has to be convened with the print and electronic media on the implementation of the program.

At the village level/Habitation Health Planning Team(HHPT) the School Health Coordinators (HM& Paramedical Staffs) / Teachers /SMC/ ASHA Workers / Anganwadi Workers/ Village Organization (Indira Kranti Padhakam) and Swachchata Doot are to be involved to implement the programme.

- School level Meeting: the activities  to be taken of Two days before the program:

The concern SWASTHH school coordinator i.e. (Head Master and paramedical staff) has to conduct meeting with the School staff ASHAs, Anganwadi workers, Panchayat secretary, VS & VRO, Children’s and chinnari doctors with SMC, and other community organizations and ensure that the message of celebration has to reach the public through different activities such as tom-tom publicity, public meetings and SMS messages 2 days prior to the activities.

- The activities to be taken of one day before at School:

Ensure that the surrounding of the school to be cleaned and properly sanitized for the celebration of the SWASTHH on Wheels. And the arrangement has to be made for the Exhibiting stalls, for the,

- Science Exhibition.

- Medical Stalls, Displaying IEC Material of the programme.

- Yuva Chaitanyam (ARSH awareness).

- ICDS Nutrition stalls.

- First Aid Center.

- 108, 104 Vehicles and their timely use.

- Awareness on Arogya Shree and also if possible a camp.

- Tom -Tom to be followed on the day.

- On the Day of Programme at the School:

- The School committee convene by the School Health Coordinator will organize a Meeting with public leaders of the Mandal, Mandal level officers, and parents of the children, NGOs and Community organizations.

- During the meeting the following topics will be included in the speeches of dignitaries to explain,

  - The aims and objectives of SWASTHH on Wheels

  - School children Drop outs / Incentives to the Children.

  - Percentage of absentees and reasons.

  - Particulars of irregular and drop out children’s

  - Success stories regarding treatment (Medical & surgical).

  - Academic innovative activities.

  - Aarogya Club/Chinnari Doctors role play system.

  - Appreciation and awards to the children with 100% attendance.

  - Badges to 1st, 2nd, 3rd rankers of each class.

  - Any other innovative awards.

  - Health Education activities on all National programs including JBAR.

- Mention about the following activities on which awareness to be generated for

Whole communities

- De worming

- Weekly Iron Folic Acid Supplimentation(WIFS)

- Hand washing

- Menstrual Hygienic

- Nutrition/Anemia – Prevention

- Personal Hygienic-THEN HE

  - T: Teeth & Tongue

  - H: Head & Hair

  - E: Ear & Eyes

  - N: Nose & Nails

  - H: Heart & Hands

  - E:  Equipment

- Life Skills

- Reproductive Track Infections

- Child Marriages

- Child Labour

- Using Toilets with Running Water

- Napkin Preparation

- Parental Trainings

- Aids and Appliances

- Strengthening of Aarogya Clubs

The SWATTH on Wheels vehicle will bring awareness on the points mentioned in the 2.2 through PAS. during morning and evening hours.

3 pm to 4 pm conclusion and closing ceremony and documentation.

- Next Day of the Programme:

The H.M of the School has to submit the documentation of the celebration (2 copies) to the District JBAR Coordinators and SHC through Mandal education Officer for on words submission to the District to the State on or before 31st of January 2013 along with SOEs.

Monitoring the SWASTHH on Wheel.

- At The districts level the implementation of the program will be monitored by district collector with the help of DMHO, PO RVM, DEO and SERWS.

- The District JBAR Coordinator and SHC should prepare route map along with detailed guidelines and day to day activities with approval of the District Collector, DM&HO, PO (RVM) and D.E.O to monitor the programme.

- The District JBAR Coordinator District School Health Coordinator should identify CHNC wise one resource person for the Child Holistic Improvement Programme from DRG list. (List is Available at AMO, RVM) to promote the SWASTHH on Wheel activities by involving the CCC (Core Commitments for Children).

- The PO (RVM) and D.E.Os are requested to issue required instructions and provide necessary physical and financial requirement to MEO and H.Ms to celebrate SWASTHH on Wheels similar to *school anniversary day* celebrations at the SWASTHH schools.

Schedule of route (Road) Map to monitor the activity for the Districts JBAR/SH coordinators it should submit immediately as early as possible.

Proforma-I

| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SN | Name of the CHNC/Contact Num: | Name of the Mandal/Contact Num: | Name of the PHC/UHC/Contact Num: | Name of the SWASTTHA School | Date of activity | Persons to be involved | Name of Activity (Education)/Contact Num | Name of the Activity Coordinators (Health)/Contact Num | Activities |

Further the DM&HO & PO (RVM) and JBARC& SHC is requested to send the proforma II after

Completion of the activities.

PROFORMA – II ( to be submitted on or before 31st January 2013)

| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sl.No. | Name of the CHNC and contact num | Name of the Mandal/MEO contact num | Name of PHC/UHC/MO contact num | Name of Swasthh School (conducted) | Date of activity conducted | Persons involved | Name of Activity Coordinator (Health)/ contact No | Name of Activity Coordinators (Education) contact No | Activities conducted | 2 days before | 1 day before | On the day | Submission SOS |

Mission Director (NRHM)

O/o Commissioner of health & Family Welfare

A.P, Hyderabad

To

All District JBAR School Health Coordinators in the State

All DM&HOs in the State

All PO (RVMs) in the State

All D.E.Os in the state

All PD ICDS in the state

All District Collector and Magistrates

Copy to

Director of Public Health, AP, Hyderabad

Commissioner APVVP, Hyderabad.

Director of Medical Education, A.P., Hyderabad

Copy submitted to,

SPD (RVM) AP. Hyderabad

Commissioner of Women development & Child Welfare, A.P. Hyderabad.

Commissioner of Tribal Welfare, A.P Hyderabad.

Commissioner and DSE A.P, Hyderabad